## Task Log Programming
Date | Start | End | Interuption | Time (H:M:S) | Estimate | Task
2019-02-12 | 14:30 | 14:36 | 0:00 | 0:06 | 0:10 | Setting up the Task Log
2019-02-12 | 14:36 | 14:38 | 0:00 | 0:02 |  | Setting up Journal
2019-02-26 | 13:25 | 15:29 | 0:02 | 2:02 | 3:30 | Making the Menu
2019-02-26 | 15:30 | 15:33 | 0:00 | 0:03 |  | Exporting the Package
2019-03-05 | 11:32 | 18:59 | 0:06 | 7:20 | 6:00 | Making the Driving Package
2019-03-05 | 19:02 | 19:11 | 0:00 | 0:08 | 0:05 | Exporting the Package
2019-03-12 | 13:16 | 15:21 | 0:05 | 2:00 | 1:30 | Making the First Person Controller
2019-03-12 | 15:26 | 15:36 | 0:03 | 0:07 | 0:05 | Exporting the Package
2019-04-16 | 16:27 | 20:34 | 0:44 | 3:23 | 3:30 | Making the wall Package
2019-04-16 | [5 empty] | Exporting the Package
2019-04-23 | 16:00 | 20:17 | 0:39 | 3:37 | 3:03 | Making the Camera swap Pack
2019-04-23 | 20:18 | 20:20 | 0:00 | 0:03 | 0:05 | Exporting the Package
2019-05-03 | 17:16 | 17:48 | 0:00 | 0:17 | 0:15 | Finishing Logs and Journal
| Total Estimate |  |  |  | 18:13
| Total Time |  |  |  | 19:08
| Estimate Error |  |  |  | 1.0502

## Journal
Date | 2019-02-12 | 2019-02-26 | 2019-03-05 | 2019-03-12 | 2019-04-16 | 2019-04-23 | 2019-05-03
Tasks | Set up the Task Log and Journal (Re using my old one, just adding some new columes and volumes. New programming to Excel also added ) | I tried to upload pics to explain what needs to be done, but I didn't count in the image process takes so much time | For some reason, the car was too heavy to controll and the fun is just missing, I dropped down the Mass but it really isn’t helping much. I have to look into this more to find out what to do. | I missed making first person controlls, for a very long time I was wondering why my character is just falling, then remembered there is no rigitbody or anything really. | The wall trigger just wouldn't work, I couldn't figure out why that was. So I did what a real engineer would do, I turned it off and on again! I deleted the box colider and made a new one. It worked like a charm | At first I thought this would be easy, its just switching on and off camera, but soon I realised the way I had it programmed it would just switch once. I changed the location of my programing to voide update, that just made it switch constantly. That was a huge shocker (not really, just my stupidity) then I began to look at the code from completley new direction. Everything start to work like clock gear falling into place. It was very sweet ending. | Note to self: Read all the requirment for the CW, I realised I needed to upload some new information, last minute editing is least of my favs, but what needs to be done, needs to be done!